## Sheet1
|  | Activity | Week(s) |  |  | Start date | Predecessor
Planning and Requirement |  |  | 2
| Planning |  |  | 0.5
| Requirement Gathering |  |  | 0.5 |  |  | 3
| Requirement Speicifcation Analysis |  |  | 0.5 |  |  | 4
| Requirement Validation |  |  | 0.5 |  |  | 5
Build 1 |  |  | 10 |  |  |  | 2
| Design and Development |  |  | 7 |  |  | 6
|  | Product listing |  |  | 3 |  | 6
|  | Member registration |  |  | 3 |  | 6
|  | Staff management |  |  | 1 |  | 6
| Testing |  |  | 2 |  |  | 9
|  | Unit testing |  |  | 1 |  | 12
|  | Integration testing |  |  | 2024-06-07 |  | 12
|  | User Acceptance Testing (UAT) |  |  | 2024-01-07 |  | 12
| Implementation |  |  | 1 |  |  | 13
|  | Deploy into production |  |  | 2024-03-07
|  | Testing in deployed environment |  |  | 2024-04-07
Build 2 |  |  | 11 |  |  |  | 8
| Design and Development |  |  | 8
|  | Ordering |  |  | 3
|  | Payment |  |  | 3
|  | Table reservation |  |  | 2
| Testing |  |  | 2
|  | Unit testing |  |  | 1
|  | Integration testing |  |  | 2024-06-07
|  | User Acceptance Testing (UAT) |  |  | 2024-01-07
| Implementation |  |  | 1
|  | Deploy into production |  |  | 2024-03-07
|  | Testing in deployed environment |  |  | 2024-04-07
Build 3 |  |  | 10
| Design and Development |  |  | 7
|  | Delivery |  |  | 1
|  | Report generation |  |  | 1
|  | Membership |  |  | 3
|  | Promotion |  |  | 2
| Testing |  |  | 2
|  | Unit testing |  |  | 1
|  | Integration testing |  |  | 2024-06-07
|  | User Acceptance Testing (UAT) |  |  | 2024-01-07
| Implementation |  |  | 1
|  | Deploy into production |  |  | 2024-03-07
|  | Testing in deployed environment |  |  | 2024-04-07

## Sheet2
Payment Module Requirements
1.0 Authenticate user
| 1.1 | - | The system shall authenticate users before allowing access to the payment module.
| 1.2 | - | The system shall support multiple authentication methods.
2.0 Process payment |  | -
| 2.1 | - | The system shall support payments in multiple currencies.
| 2.2 | - | The system shall display payment amounts in the user's preferred currency.
| 2.3 | - | The system shall process payments in the user's preferred currency.
| 2.4 | - | The system shall ensure that the total transaction amount is accurate.
| 2.5 | - | The system shall integrate with multiple payment gateways.
| 2.6 | - | The system shall process payments in real-time.
| 2.7 | - | The system shall provide immediate feedback to users on the status of their payment.
| 2.8 | - | The system shall allow users to save payment methods for future use.
3.0 Generate receipts and notifications |  | -
| 3.1 | - | The system shall generate receipts for successful payments.
| 3.2 | - | The system shall email receipts to users.
| 3.3 | - | The system shall send push notifications for completed transactions.
| 3.4 | - | The system shall send SMS confirmations for completed transactions.
4.0 Refunds |  | -
| 4.1 | - | The system shall allow users to request refunds within 12 hours.
| 4.2 | - | The system shall allow users to enter reason when requesting refunds.
| 4.3 | - | The system shall allow staff to view user refund requests.
| 4.4 | - | The system shall allow staff to approve or deny user refund requests.
| 4.5 | - | The system shall display the request status to the user.
| 4.6 | - | The system shall automate the refund process after approval.
| 4.7 | - | The system shall update a new transaction status after a refund is processed.
5.0 View transaction history |  | -
| 5.1 | - | The system shall provide users with access to their transaction history.
| 5.2 | - | The system shall allow filtering of the transaction history.
| 5.3 | - | The system shall allow searching within the transaction history.
product
1.0 Manage Product Information |  | -
| 1.1 | - | The system shall allow staffs to add new products.
| 1.2 | - | The system shall allow staffs to update product information.
| 1.3 | - | The system shall allow staffs to delete products.
| 1.4 | - | The system shall display a list of all products.
| 1.5 | - | The system shall display detailed information for each product, including name, description, price, and images.
| 1.6 | - | The system shall categorize products into different categories for easier navigation.
-
2.0 Navigate the Menu of Products |  | -
| 2.1 | - | The system shall display real-time product availability status.
| 2.2 | - | The system shall allow users to exclude products that contain their allergies.
| 2.3 | - | The system shall allow users to browse products by categories.
| 2.4 | - | The system shall allow users to search for products by any keywords.
| 2.5 | - | The system shall allow users to filter products by price range, category, and other attributes.
| 2.6 | - | The system shall display search results based on user queries.
| 2.7 | - | The system shall display product recommendations based on user preferences and purchase history.
| 2.8 | - | The system shall allow users to read product details page for the selected product.
| 2.9 | - | The system shall display other related products on the product detail page.
-
3.0 Post Reviews and Ratings |  | -
| 3.1 | - | The system shall allow users to submit reviews for products.
| 3.2 | - | The system shall allow users to rate products.
| 3.3 | - | The system shall display product reviews and ratings to other users.
| 3.4 | - | The system shall allow staffs to moderate and delete inappropriate reviews.